## Tracker
Track Installation
Segment | Planned Mi | Completed Mi (Previous) | Completed Mi (Current) | % Completion | Completed Mi % (Previous) | Completed Mi % (This Week) | Notes
Central Urban Corridor | 19 mi | 12 mi | 16 mi | 84% | 63.16% | 21.05% | Advanced machinery and night shifts increased pace. Monitor potential community noise concerns.
Southeastern Quadrant | 15 mi | 6 mi | 10 | 66.66% | 40% | 26.67% | Recent equipment upgrades significantly improved installation rate. Continued focus on maintaining momentum.
Eastern Section | 12 mi | 6 mi | 6 | 50% | 50% | 0% | No progress due to rocky terrain. Exploring alternative methods and potential rerouting. Strategic review needed.
Western Industrial Area | 22 mi | 9 mi | 16 mi | 73% | 40.91% | 31.82% | Accelerated progress with enhanced equipment deployment. Optimize resource allocation to sustain pace.
Electrification
Component | Planned Units | Completed Units (Previous) | Completed Units (Current) | % Completion | Completed Units % (Previous) | Completed Units % (This Week) | Notes
Track Electrification | 68 mi | 24 mi | 30 | 50% | 30% | 8.824% | Significant progress with 6 mi electrified recently. Continuing efforts to stay on track.
Substations Construction | 5 | 2 | 2 | 40% | 40% | 0% | No new substations completed. Delay in electrical components impacts schedule.

## Dashboard
Metroville Urban Rail Expansion Project Dashboard
| Current Spent |  | Budget |  | Track Installation (%) | Electrification completion (%) |  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Phase 1
[9 empty] | Phase 2 | [6 empty] | ←Illustrative
| 90M |  | 125M |  | 50% | 40% |  |  | Phase 3
Phase 4
PHASE 1
| Progress - Completion % | [12 empty] | Project Financials
| Status Update | [5 empty] | Challenges
| Electrification progress |  |  | Track Installation Status |  |  | - Eastern section in risk - Delay due to rocky terrain - 6mi behind schedule ACTION: in progress evaluation of alternative method to expedite progress. - Overspent in the excavation ACTION: Savings on materials have offset this, keeping us within 5% of our overall budget projection for this phase. - Substations construction: Delay in electrical components ACTION: action plan in progress with Buyer
| • 30 of 68 miles completed • 6 miles added this period • Phase 1 progressing steadily |  |  | • Eastern Section delayed by terrain • Southeastern: 10 of 15 miles completed • Efficiency improved after upgrade
Community & Cost Status
• Positive community engagement • Noise concerns under review • Costs controlled within 5% variance
| Community Feedback Highlights | [6 empty] | Relevant Risks Schedule slippage and cost escalation in the Eastern Section, compounded by terrain challenges, community constraints, and supply-chain delay
Efforts to engage with the community have been well-received, with many expressing appreciation for our transparency and the opportunity to voice their concerns.
Significant increase in complaints about nighttime construction noise in the Eastern Section. Residents are requesting that we limit work to daytime hours.
Add electrification progress
Add budget tracking

## Sheet2
Budget (INR M)
125
Current Spend (INR M)
90
Grand Total
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Sheet1
Category | Amount (in Million)
Actual Spent | 90
Projected Budget | 125
Project Area | Issue / Risk | Impact | Current Status | Action / Mitigation Plan
Eastern Section | High risk due to terrain conditions | 6 miles behind schedule | In progress | Evaluation of alternative construction methods to expedite progress
Eastern Section | Overspend in excavation activities | Cost pressure | Controlled | Savings on materials have offset costs, keeping spend within 5% of budget
Substation Construction | Delay in electrical component delivery | Schedule delay | In progress | Action plan being coordinated with procurement buyer
|  | Metric Type | Metric Name | Value
|  | Financial | Budget (INR M) | 125
|  | Financial | Current Spend (INR M) | 90
|  | Progress | Electrification Completion (%) | 44
|  | Progress | Track Installation Completion (%) | 67
|  | Project | Current Phase | Phase 1